Contents

List of Abbreviations and Key Concepts 	5

Background	9

1.	Introduction	11

1.1	Objective of the Manual	11

1.2	DANCEE Programme - Strategy, Priorities 
and Criteria for Support	12

1.3	Organisation of the Manual	17

2.	Project Preparation	19

2.1	Two Types of Projects	19

2.2	Project Identification	19

2.3	Project Preparation for Tendered Projects	22

2.4	Project Preparation for Application Projects	24

2.4.1	Submission of Ideas	24

2.4.2	The Formal Application	26

2.4.3	Approval of Application	26

3.	Award of Projects	29

3.1	Differences Between the two Models for Awarding 
Projects	29

3.2	Award of Projects by Application	29

3.3	Award of Projects by Tender	30

3.3.1	Rules and Procedures for Award of Contracts	30

3.3.2	Standard Contract Forms	33

3.3.3	Eligibility	34

3.3.4	DEPA’s Manual for Tendering and Contracting	35

4.	Project Implementation	37

4.1	Key Stakeholders in Project Implementation	37

4.1.1	The Project Holder	37

4.1.2	The Beneficiary	39

4.1.3	The Ministry of Environment	40

4.1.4	DANCEE	40

4.2	Management Forums	41

4.2.1	Project Management Group	41

4.2.2	Steering Committee	41

4.2.3	Advisory Committee	43

4.3	Project Monitoring and Reporting	43

4.3.1	Project Monitoring Systems	43

4.3.2	Reporting	46

4.3.3	Baseline Descriptions	47

4.3.4	Approval of Reports	49

4.3.5	Inception Report	49

4.3.6	Procedures Manual	51

4.3.7	Progress Reports	52

4.3.8	Technical Reports	54

4.3.9	Completion Report	55

4.4	Financial Management	57

4.4.1	Financial Management	58

4.4.2	Payment Schemes	58

4.4.3	Terms of Payment	60

4.4.4	Financial reporting	60

5.	Evaluation	63

5.1	Framework for Evaluation	63

5.2	Evaluations Carried Out by External Consultants	65

5.2.1	Terms of Reference	65

5.2.2	Contracting	65

5.2.3	Implementing the Evaluation	65

5.2.4	The Evaluation Report	68

5.3	Lessons Learned	68

5.4	Inspection and Examination of Projects	68

Enclosure A –	Project Idea Format	71

Enclosure B –	Project Document Format	75

Enclosure C –	Terms of Reference Format	97

Enclosure D –	Appraisal Report Format	103

Enclosure E –	Guidelines for Steering Committee Meetings	107

Enclosure F –	Covering Letter to Progress Report	111

Enclosure G –	Letter of Confirmation	115

Enclosure H –	List of DANCEE Indicators	119

Enclosure I –	References	123

List of Abbreviations and 
Key Concepts

AC	Advisory Committee

BAT	Best Available Technology

CEEC	Central and Eastern European Countries

DANCEA	Danish Cooperation for Environment in the Arctic (DEPA division)

DANCEE 	Danish Cooperation for Environment in Eastern Europe (DEPA division)

DANCED 	Danish Cooperation for Environment and Development (DEPA division)

DANIDA	Danish International Development Assistance (Ministry of Foreign Affairs)

DEPA 	Danish Environmental Protection Agency

DESF	Danish Environmental Support Fund for Eastern Europe

DKK	Danish Kroner (Danish currency)

EDRF	Environment and Disaster Relief Facility

EKF	Danish State Export Credit Agency

EU	European Union

IPPC	Integrated Pollution Prevention Control (EU Directive)

IØ	Investment Fund for Central and Eastern Europe

LFA	Logical Framework Approach

LPC	Local Project Coordinator

M/M	Man Month

MoE	Ministry of Environment in the partner country

MoEE	Danish Ministry of Environment and Energy

MKØ	Environmental Soft Loan Programme for Eastern Europe (administered by EKF)

NEAP	National Environmental Action Plan

NEHAP	National Environmental Health Action Plan

NEFCO	Nordic Environment Finance Corporation

NGO	Non-Governmental Organisation

NIS	Newly Independent States

NPAA	National Programmes for the Adoption of the Acquis

PIP	Project Implementation Plan

SC	Steering Committee

ToR	Terms of Reference

UN	United Nations

Appraisal

Overall assessment of the relevance, feasibility and sustainability of a project prior to decision on funding.

Beneficiary

An organisation in a Partner Country which benefits from the project and which receives the result of the project after completion. The term “beneficiary” is broadly defined and may include public and private enterprises, government authorities, NGOs, etc.

Contact Person

A contact person in MoE who is responsible for coordinating the cooperation between DANCEE and MoE.

Country Coordinator

A DANCEE specialist employed by DEPA, responsible for cooperation with the partner country on DANCEE supported projects.

Effectiveness

A measure of the extent to which a project or programme achieves its objectives.

Efficiency

A measure of the “productivity” of the implementation process - how economically inputs are transformed into outputs.

Evaluation

An independent examination of a project or programme, partly to determine its results, efficiency, effectiveness, impact, relevance and sustainability, and partly to draw lessons that may be more widely applicable.

Letter of Grant (Tilsagnsskrivelse)

A document issued by DANCEE to an applicant granting a specific amount of money for implementation of a project according to the application (the project document). After acceptance by the applicant, the letter of grant, with its terms and conditions, constitutes an agreement regarding the implementation of a project.

Local Project Coordinator

A local specialist employed by DEPA to coordinate DANCEE activities in a partner country.

Local Project Director

A senior manager appointed by MoE to be responsible for the overall implementation of the project.

Local Project Manager

A person appointed by the beneficiary having day-to-day responsibility for project implementation.

Logical Framework Approach

An objective-oriented management tool used to plan, execute and evaluate programmes and projects.

MoEE Specialist

DANCEE may appoint a specialist from the Danish Ministry of Environment and Energy (MoEE), e.g. from one of DEPA’s specialised divisions or from one of MoEE’s Agencies to represent DANCEE in specific projects.

Monitoring

Continuous or periodic surveillance of the progress of a programme or project.

Partner Country

One of the countries selected to receive DANCEE assistance.

Project Document

The project document describes the objectives, outputs and activities of a project, relevant policies and external support. The project document also specifies the terms and conditions for the implementation of a project, and the responsibilities of the project holder and the beneficiary.

Project Holder

An organisation (private enterprise, parastatal, government or non- government institution), which has been awarded a contract after tender or a grant after application.

Project Management Group

The group responsible for day-to-day project management. Normally the group consists of the local project manager and the team leader.

Review

A comprehensive assessment of a programme or project during implementation.

Team Leader

A person appointed by the project holder and approved by DANCEE. The team leader has direct daily responsibility for the timely and correct implementation of the project according to the project document.

Background

In April 1991, the Act on Subsides for Environmental Activities in Eastern European Countries was adopted by the Danish Parliament. The Danish Environmental Support Fund for Eastern Europe (DESF) was subsequently established.

In 1993, the DESF was incorporated into the new Environment and Disaster Relief Facility (EDRF), a new Danish facility for the support of environment and disaster areas in Eastern Europe and developing countries. This initiative was based on the changes in Europe after the collapse of the Berlin Wall in 1989 and to follow-up the intentions from the UN Conference in Rio on Environment and Development in 1992. The intention is to annually increase funds to support environmental and disaster issues until the total Danish support constitutes 0,5 % of Gross National Income in year 2005. Funds are distributed fifty-fifty to environmental and disaster issues respectively.

In October 1993, the “Strategy for Environmental Activities in Eastern Europe” was drawn up and has been the basis for environmental assistance to Eastern Europe. The DESF was administered by the Danish Environmental Protection Agency (DEPA).

From 1999, the name of the EDRF was changed to the Environment, Peace and Stability Facility. The environmental part of the facility is supporting projects in Eastern Europe, specific developing countries and the arctic regions. At the same time the name DESF has been changed to Danish Cooperation for Environment in Eastern Europe (DANCEE), still administered by DEPA.

The funds for developing countries administered by DEPA is administered by the Danish Cooperation for Environment and Development (DANCED). Funds for the arctic region are administered by the Danish Cooperation for Environment in the Arctic (DANCEA), a DEPA division.

Denmark's environmental assistance under the Environment, Peace and Stability Facility comprises not only the DANCEE Programme  but also - in 1994-96 - environment-related sectoral assistance and the Green Investment Facility under the Investment Fund for Central and Eastern Europe (the IØ Fund). From 1998, the environment-related sectoral assistance is designated sector-integrated environmental assistance and is an element of the Government's Baltic Sea Initiative in the environment sector. From 1998, the environmental assistance are supplemented with the Environmental Soft Loan Programme for Eastern Europe (MKØ), administered by the Danish State Export Credit Agency (EKF).

Denmark's assistance in the environment sector is co-ordinated by the Danish Environmental Protection Agency (DEPA), in that DEPA discusses the sectoral programmes with the ministries and agencies implementing them and guides the environmental approach. DEPA is also the consultation party on the environmental aspects of projects under the IØ Fund's Green Investment Facility. Lastly, DEPA has a seat on the board of Nordic Environment Finance Corporation (NEFCO). Many Danish players with different expertise thus work together and supplement each other's environmental activities.

Grants to environmental assistance in Eastern Europe from 1996 to 1999.

| DKK million | 1996 | 1997 | 1998 | 1999 |
| --- | --- | --- | --- | --- |
| DANCEE | 300 | 430 | 400 | 500 |
| Sector Integrated Env. Ass. | 100 | 100 | 140 | 175 |
| “Green Facility” (IØ) | 100 | 100 | 70 | 70 |
| “Soft Loans” (MKØ) |  |  | 45 | 60 |
| Total | 500 | 630 | 655 | 805 |

# Introduction

This project cycle management manual replaces the publication “Projektforslag til miljøaktiviteter i Øst- og Centraleuropa. Orientering fra Miljøstyrelsen, nr. 14, 1995”.

## Objective of the Manual

Project cycle management

Project cycle management is the process of developing and managing a project from the initial idea to the final evaluation of the project’s results. A project is defined as a planned undertaking designed to achieve certain specific objectives within a given budget and within a specific period of time.

The purpose of the manual

The purpose of this Project Cycle Management Manual (the Manual) is to provide information on project cycle management procedures for projects supported by DANCEE.

The target group

The primary target group of the Manual is the Ministry of Environment (MoE) and environmental funds in the partner countries and potential project holders, e.g. consultants, institutions, Non-Governmental Organisations (NGOs), and enterprises, and their local partners and beneficiaries in the partner countries.

Donor organisations and international banks are the secondary target groups. The Manual should facilitate the co-financing of DANCEE support and support from other donors and international banks.

Two administrative models are applied in connection with environmental projects supported by DANCEE.

The application model

The application model is typically used by a Danish company or organisation in coorporation with a beneficiary in the partner country. This partnership identifies and describes a project according to DANCEE’s guidelines for application - please refer to Section 2.4. Subsequently, the Danish organisation or company applies to DEPA for DANCEE support.

The tender model

In the tender model, DANCEE and MoE identify a project portfolio within the framework of the country programme - please refer to Section 2.3. The identified projects will subsequently be tendered according to DEPA’s official tendering procedures.

The two models are designed to complement each other. The tender model allows DANCEE and MoE full control with the project portfolio, whereas the ideas for applications are initiated outside the formal ministerial collaboration.

Project holder

The term “project holder” is used in the Manual to describe an organisation (private, parastatal, government or non government institution), which has been awarded a contract after tender or a grant after application.

The aim of the Manual

The aim of the Manual is to facilitate the transparent and efficient development and management of DANCEE supported projects. The Manual will inform project holders about requirements for project preparation and implementation under DANCEE.

Furthermore, the Manual should assist project holders to undertake a more efficient preparation and implementation of projects. To achieve this aim, the Manual outlines a set of flexible but standardised guidelines for project preparation, award of projects, implementation and evaluation. Where necessary, projects may deviate from the guidelines, on DANCEE’s initiative or based on a specific written agreement.

The project cycles for the two project models (application and tender model) differ to some extent. In particular, the responsibilities of DANCEE and the project holders differ in the project preparation process. However, DANCEE has harmonised the administrative procedures for the two models to the largest extent possible. The Manual will describe the procedures and guidelines in general. Differences between the two project models will be mentioned explicitly where appropriate and necessary.

The Manual is based on the terminology and the processes of the Logical Framework Approach (LFA).

## DANCEE Programme - Strategy, Priorities and Criteria for Support

Strategy

The Danish government’s strategy for environmental efforts in CEEC focuses on the Baltic Sea Region, EU accession, implementing international conventions, strengthening environmental awareness in the countries and increasing efforts in the Newly Independent States (NIS-countries).

The strategy takes into account the international environmental strategies resulting from the Conferences of the European Ministers of Environment held in Dobris in March 1991, in Lucerne in April 1993, in Sofia in October 1995 and in Århus in June 1998.

Overall objectives

The overall objectives of DANCEE support are:

- to contribute as much as possible towards protection of the environment and nature in CEEC and to limit regional as well as global pollution,

- to contribute to the preparation for countries applying for EU membership for EU accession, and to comply with the international environmental conventions,

- to contribute towards political and economic development in an environmental friendly manner; specifically to support democratic and market-based economic development in such a way that protects the environment as much as possible,

- to promote transfer of environmental knowledge and of environmental protection technology from Denmark to CEEC.

Priority areas

DANCEE priority areas cover:

- water pollution,

- air pollution,

- solid and hazardous waste,

- biological diversity and sustainable forestry,

- institutional strengthening, and EU accession.

Investment and technical assistance projects

DANCEE support may take the form of investment projects or technical assistance projects or a combination of the two. DANCEE identifies the two types of projects as follows:

Technical assistance includes:

- studies, planning and analysis,

- monitoring,

- feasibility studies, appraisals and evaluations,

- institutional strengthening.

Investment projects include:

- project design,

- construction and operation,

- the supply of equipment.

The Manual describes the standard procedures covering both investment and technical assistance projects.

Partner countries

DANCEE funds are available for projects in a number of CEECs, including: Estonia, Latvia, Lithuania, Poland, Russia, The Czech Republic, Slovakia, Ukraine, Romania, Bulgaria, and Belarus. A cooperation agreement and a country programme has been drawn up with the partner countries, and DANCEE support is provided within this framework. The country programmes are described in the publication “Danish Environmental Support Fund for Eastern Europe”, DEPA 1998.

Environmental strategies of partner countries

Support is granted to projects which are consistent with the partner country’s environmental strategy as described in e.g. the National Environmental Action Plan (NEAP), the National Environmental Health Action Plan (NEHAP), and National Programmes for Adoption of the Acquis (NPAA). NPAA is prepared by a country applying for membership of the European Union (EU) and is the national plan for transposition and implementation of EU legislation. Most applicant countries have also developed sector strategies for implementing EU environmental legislation.

Criteria for support

DEPA has developed a number of criteria to determine which environmental projects may receive DANCEE funding. The criteria are outlined below and in Enclosure B of the Manual.

Needs of beneficiaries

A crucial criterion for DANCEE support is that projects reflect the needs and wishes of the beneficiary. It is essential to the success of a project that it is understood from the beginning which services and products are of interest to the beneficiary. The term “beneficiary” is broadly defined and may include public and private enterprises, government authorities, NGOs, etc.

Comformity with national and EU legislation

It is a key criterion for DANCEE support that the support conforms to the requirements of the environmental legislation of the partner country. Furthermore, support to countries applying for EU membership must contribute to the preparation of these countries for EU accession. At a minimum these projects in the EU candidate countries must be in compliance with the EU environmental legislation and other relevant EU standards.

Pollution reduction and environmental protection

The anticipated pollution reduction of a project constitutes another important criterion. Pollution reduction is measured in terms of quantity and toxicity. Projects which imply a significant quantitative and/or qualitative improvement of the environment and health standards are given high priority. However, technical assistance projects may be given just as high priority as an investment project if the projects are essential to the solution of environmental problems. Furthermore, priority is given to projects in geographical areas with serious environmental or health problems and to areas of particular natural value.

Focus on the prevention of environmental problems

Environmental problems are closely associated with the volume and structure of production and consumption. Therefore, projects should seek to attain savings in the consumption of raw materials, energy and water. Focus should be on pollution prevention, conservation,

cleaner technologies and recycling, rather than on the reduction of existing pollution.

Sustainable management of nature and forest resources

It is crucial that the transition period from planned economy to market economy does not lead to a general degradation of natural resources, as these form a prime basis for long term economic growth and development in the region. Therefore, DANCEE supports the sustainable management of nature and forest resources within four main categories:

- the management, use and protection of biodiversity,

- sustainable forest management,

- the development of eco-tourism,

- environmental education and public awareness.

Benefits to the environment and the economy

When considering pollution prevention, the interrelation between pollution and economic development is important. The Central and Eastern European Countries (CEEC) are in a difficult process of economic transition. Benefits to both the environment and the economy may be realised if environmental projects can be integrated into the on-going economic restructuring process. Priority will be given to projects which demonstrate financially and technologically appropriate solutions to environmental problems.

Danish know-how and technology

DANCEE support is primarily granted to projects which entail the transfer of Danish know-how and/or technology. As a general rule, only projects involving proven technologies will be approved. Projects involving the development of new technology may, however, be considered in exceptional cases.

Projects of general interest

Projects of general interest and utility, possessing the potential for being replicated, are given preference over projects of interest only to a limited number of potential project holders. All projects should include carefully designed activities contributing to the dissemination of project results, either in the form of workshops, articles in journals or similar activities. All projects must also provide a brief summary (ex-ante and ex-post) of project implementation. These summaries are used in DANCEE annual reports and are posted on the DANCEE Internet homepage. Further, plant and major equipment supplied for projects should be clearly marked to acknowledge DANCEE financial support.

Project sustainability

The degree of sustainability of a project is bound up with a number of factors, such as:

- political support for the project,

- appropriate choice of technology,

- institutional and managerial capacity of the beneficiary,

- economic and financial considerations.

A project’s sustainability can be assessed in terms of the project’s ability to continue operations and to sustain the environmental improvement even after the withdrawal of donor support. Priority is given to projects which are likely to have a high degree of sustainability.

Co-financing

DANCEE funding is perceived as a means of promoting self-support. As such, projects involving the beneficiary’s own funds or in-kind contribution, whether the beneficiary is an enterprise or a governmental agency, will be given priority over projects which rely solely on DANCEE support. Projects whose subsequent phases are likely to be financed by other sources - the beneficiary’s own funds or funding from other donors or international financing institutions - will also be given high priority.

Three typical funding models are applied:

- projects financed solely by DANCEE, usually technical assistance projects and small investment projects,

- projects in the range of Euro 0.5 - 6 million, where co-financing is likely to come from the beneficiary and from national and international financial institutions and funds,

- large scale projects, expected to be funded by international financial institutions, which may be kick-started by Danish inputs through feasibility studies for example.

## Organisation of the Manual

The DANCEE project management cycle

DANCEE’s project management cycle has four phases. These are illustrated in the diagram of the project cycle shown in Figure 1.1. Each phase of the project management system is described in a separate chapter of the Manual.

Figure 1.1

DANCEE Project Management Cycle

The present chapter has outlined the objectives of the Manual and has described the criteria used by DANCEE to determine which projects to support.

Chapter two

Chapter two deals with project preparation. The chapter describes the development of projects from the initial idea to the final project document. The preparation process of projects by application and of projects by tender is outlined in separate sub-sections.

Chapter three

Chapter three deals with award of projects which in principle is identical for application and tender projects. The chapter describes the procedures used for contracting by DEPA and the standard conditions and responsibilities of the project holder.

Chapter four

Chapter four deals with project implementation. The chapter outlines the suggested project management structure and contains guidelines and procedures for reporting and monitoring.

Chapter five

Chapter five deals with project evaluation. The chapter describes DANCEE procedures for evaluation and contains guidelines for reviews, end-of-project and ex-post evaluation.

# Project Preparation

## Two Types of Projects

Awarding projects

Projects within the DANCEE programme can be identified and awarded in two different ways:

- the application method (“projects by application”)

- the tender method (“projects by tender”)

In short, projects by application are identified by a Danish company or organisation in cooperation with a beneficiary. Projects are awarded to the project holder on the basis of an application from the project holder and in the form of a grant.

A project by tender is identified by DANCEE in cooperation with MoE, and awarded to the project holder in the form of a contract to a tenderer.

Below the project preparation cycles are described for tendered projects and for projects by application.

## Project Identification

The project identification procedure is shown in Figure 2.1.

Country programme

Denmark co-operates a number of CEECs - please refer to Section 1.3. In each country, a cooperation agreement and a country programme have been drawn up by DEPA and MoE.

The country programme is an agreement between MoE and DEPA describing sector priority areas in the individual country (e.g. water pollution, hazardous waste, air pollution, EU approximation) and project proposal procedures. The country programme is the basis upon which both projects by tendering and projects by application are prepared.

The country programmes are presented in the publication “Danish Environmental Support Fund for Eastern Europe”, DEPA 1998. This publication will be updated regularly. Lists of all on-going and completed projects for each partner country will be available on DEPA’s homepage http://www.mst.dk

Figure 2.1

Project Identification Procedure

Project long-list

A project long-list is prepared by DANCEE and MoE for all partner countries and is continuously updated. The list contains project ideas and project documents formulated by DANCEE and MoE, as well as project ideas and project documents submitted by applicants. The project long-list is not prioritised.

The project long-list is gradually reduced to a prioritised project short-list when DANCEE and MoE assess project ideas and project documents.

The project long-list is jointly assessed by DANCEE and MoE at least twice annually. The assessment includes an analysis of how the projects comply with the current priorities of the partner country, DANCEE’s criteria for support, and the sector priority areas agreed in the country programme.

Project short-list

Based on the assessment of project ideas and project documents from the project long-list, DANCEE and MoE agree on a project short-list. This list constitutes the prioritised project pipeline which DANCEE and MoE intend to initiate during the following year.

Both the project long and short-lists are internal working papers for DANCEE and MoE.

The process for the gradual reduction of the project long-list into the project short-list is shown in Figure 2.2.

Figure 2.2.

Preparing the Prioritised Project Pipeline

## Project Preparation for Tendered Projects

DANCEE is responsible for turning the project idea into a project document for tendered projects.

Project preparation mission

DANCEE may contract external consultants to prepare project documents, but also to participate in project preparation missions and project identification missions. DANCEE may also use external consultants for preparing appraisals. Opportunities for consultants to provide assistance are published on DEPA’s home page (http://www.mst.dk). Interested consultants may contact DANCEE for registration of their interest.

The project document will normally be designed by a team of national and international experts with relevant expertise. The team will work according to Terms of Reference (ToR) worked out by DANCEE. The country coordinator or a Danish Ministry of Environment and Energy (MoEE) specialist will meet the project identification team to discuss the ToR. An ToR outline of the different project preparation missions is attached as Enclosure C.

Project document

The experts will prepare the project document using the LFA and the result will be presented in the format shown in Table 2.1. The project document can also be prepared as part of the feasibility study. For further explanation of the LFA please refer to the publications “Logical Framework Approach - A Flexible Tool for Participatory Development”, Danida 1995, and “The Logical Framework Approach”, Norad 1996.

Stakeholder analysis

The project document must include a stakeholder analysis. The stakeholder analysis will list stakeholders and beneficiaries and will describe their main interests in the project. Special attention should be given to the identification of possible conflicting interests among different stakeholders. The project document will describe how the project strategy will address conflicting interests.

Feasibility study

In connection with large and comprehensive projects, DANCEE may require that a feasibility study is carried out. The scope and level of detail of a feasibility study will depend on the complexity and size of the project. The task of undertaking feasibility studies will normally be competitively tendered.

Appraisal

Before a project document is finally approved, it is appraised internally by DANCEE, a MoEE specialist or by independent external specialists. Depending on the size and complexity of the project, DANCEE will decide whether a desk or a field appraisal should be applied. Representatives from the partner country may participate in the appraisal. The outline for ToR in Enclosure C is also used for appraisal missions.

Table 2.1

Project Document Format (identical with Application Format)

Table of contents	Max. no of pages

- The project cover sheet (see Enclosure B I)

- Map of location

- List of abbreviations

- Executive summary	2

- Context	6

  - Project idea

  - Significance of the environmental problem

  - Legal framework, EU environmental legislation, and NPAA if applicable

  - Institutional set-up, stakeholder identification and analysis

  - Prior, on-going or planned assistance to the sector

- Definition of project interventions	8

  - The development objective and corresponding indicators

  - Immediate objective and corresponding indicators

  - Outputs and corresponding indicators

  - Main activities

  - Inputs

  - Assumptions, risks and preconditions

- Compatibility with DANCEE policies and the country programme	1

  - Programme priority areas targeted by the project

  - Programme priority criteria targeted by the project

- Implementation		5

  - Project implementation plan with phases

  - Organisation and administration

  - Reporting, monitoring and reviews

  - Dissemination of project results

  - Budget

  - Accounting and Auditing

Annexes to the project document.

- LFA-matrix

- Profile of project staff

- Draft project implementation plan

- Organisational chart

- Format for budgeting and accounting (please refer to Table 4.6)

- Total budget, budget details and notes (please refer to Enclosure B2-B7)

- List of addresses

For further information, please refer to Enclosure B

The appraisal will focus on the relevance, feasibility and sustainability of the project, on its concurrence with national, EU and Danish policies, and on its compliance with priority areas and programme criteria. A format for appraisal reports is included as Enclosure D.

Final approval

Before the final approval, DANCEE must obtain a letter of confirmation from the beneficiary - please refer to Enclosure G.

Assuming a positive appraisal, the project document will be approved by DANCEE and MoE. Procedures for tendering and contracting are dealt with in Section 3.

## Project Preparation for Application Projects

### Submission of Ideas

Interested enterprises, consultants, organisations, NGOs and others are welcome to submit ideas for projects at any time. DANCEE recommends applicants to outline a project idea - using the format shown in Table 2.2. - to DANCEE in order to obtain DANCEE’s comments. In this way, applicants can spare the cost of elaborating a full-blown application in form of a project document, if the project idea is not within DANCEE’s scope or has already been carried out, etc.

The description of the project idea should as a minimum be one to two pages, including the underlined sections of Table 2.2 above. The idea must be formulated jointly with the project beneficiary.

DANCEE will give its initial assessment and comments on the project idea. The applicant can use the assessment and comments to decide whether or not the applicant wishes to elaborate on the idea and submit a formal application. The positive reception of a project idea at this stage by DANCEE does not imply that funding will eventually be made available.

Table 2.2

Project Idea Format

Table of contents	Max. no of pages

The total number of pages should not exceed 5, enclosures excluded.

- The project cover sheet (see Enclosure BI in Enclosure B)

- Map of location

- List of abbreviations

- Context	1

  - Project idea

  - Significance of the environmental, nature or health problem

  - Legal framework, EU environmental legislation and NPAA if applicable

  - Institutional set-up, stakeholder identification and analysis

  - Prior, on-going or planned assistance to the sector

- Definition of project interventions	1

  - The development objective

  - Immediate objective

  - Outputs

  - Activities

  - Inputs

  - Assumptions, risks and preconditions

  - Dissemination of project results

- Compatibility with DANCEE policies and the country programme	1

  - Programme priority areas covered by the project

  - Programme priority criteria targeted by the project

- Outline projects implementation plan	1

- Budget outline,  (See Enclosure A1)	1

Annex 1 The project organisation

(including a presentation of the applicant, its local partners and the resources of

the beneficiary organisation and stating the responsibilities of the various parties)

Annex 2 Presentation of the applicant

Annex 3 Declaration on public debt not exceeding DKK 100.000

For further information, please refer to Enclosure A.

### The Formal Application

Letter of confirmation

The application will be made by the applicant and the beneficiary in common. A Letter of Confirmation signed by the beneficiary must be enclosed with the application. DANCEE’s format for a Letter of Confirmation must be used - please refer to Enclosure G. If possible, the idea should also have been discussed with the country coordinator and the local project coordinator (LPC).

The application must be prepared using LFA and the result must be presented in the format shown in Table 2.3 and further elaborated as shown in Enclosure B. The application format is identical with the project document format shown in Table 2.1. For further explanation on the LFA, please refer to the publications “Logical Framework Approach - A flexible Tool for Participatory Development”, Danida 1995, and “The Logical Framework Approach”, Norad 1996.

Following receipt of the application by DANCEE, the applicant will receive a letter giving DANCEE’s reference number for the application and indicating the DANCEE person responsible for the assessment. DANCEE will normally decide on the merits of the application within four months of receipt. If this is not possible, the applicant will be informed in writing with a new date for the decision.

### Approval of Application

Approval and rejection of applications

Applications are jointly assessed by the country coordinator or other DANCEE specialists, other MoEE specialists, the LPC and the contact person in MoE. The assessment is based on the project’s compatibility with the country programme, the DANCEE criteria for support described in Section 1, and the partner country’s current priorities.

When the assessment process has been completed, a document of recommendation will be drafted and submitted to DEPA’s management for final approval and signature.

DANCEE will inform applicants by letter indicating approval or non-approval of the submission. In the case of successful applicants this will be a letter of grant.

Table 2.3

Application Format (identical with Project Document Format)

Table of contents	Max. no of pages

- The project cover sheet (see Enclosure B I)

- Map of location

- List of abbreviations

- Executive summary	2

- Context	6

  - Project idea

  - Significance of the environmental problem

  - Legal framework, EU environmental legislation, and NPAA if applicable

  - Institutional set-up, stakeholder identification and analysis

  - Prior, on-going or planned assistance to the sector

- Definition of project interventions	8

  - The development objective and corresponding indicators

  - Immediate objective and corresponding indicators

  - Outputs and corresponding indicators

  - Main activities

  - Inputs

  - Assumptions, risks and preconditions

- Compatibility with DANCEE policies and the country programme	1

  - Programme priority areas targeted by the project

  - Programme priority criteria targeted by the project

- Implementation		5

  - Project implementation plan with phases

  - Organisation and administration

  - Reporting, monitoring and reviews

  - Dissemination of project results

  - Budget

  - Accounting and Auditing

Annexes to the project document.

- LFA-matrix

- Profile of project staff

- Draft project implementation plan

- Organisational chart

- Format for budgeting and accounting (please refer to Table 4.6)

- Total budget, budget details and notes (please refer to Enclosure B2-B7)

- List of addresses

- Letter of confirmation (from beneficiary)

- Profile of applicant, including financial standing

- Declaration on public debt not exceeding DKK 100.000

For further information, please refer to Enclosure B.

# Award of Projects

## Differences Between the two Models for 
Awarding Projects

As mentioned in Chapter 2, projects by applications are initiated by the project holder, whereas projects by tender are initiated by DEPA.

Legal differences

From a legal point of view, the two methods differ in particular with respect to the responsibility for the project document.

Tendered projects

Since DEPA has prepared the project document in a project by tender, the responsibility for the project document rests with DEPA, and the project holder is responsible only for implementing the project in accordance with the duty of care.

Projects by application

In projects by application, the project holder is not only responsible for implementing the project, but he is also responsible for preparing the project document. This responsibility entails inter alia that the project document is founded on adequately detailed and thorough investigations and surveys of facts and circumstances surrounding the project and that the design of the project is feasible. DEPA requires the project document to be in accordance with the best professional practice. The fact that DEPA has assessed the application before a grant is awarded does not limit the responsibility of the project holder.

Advance payment

There is also a difference between the two project types with respect to advance payments made to the project holder.

In projects by application, advance payments are in general available only to NGOs, and advance payments are available to other project holders only in connection with the procurement of supplies or works.

In projects by tender, advance payments are available to all project holders.

## Award of Projects by Application

As mentioned in Section 2.4, DANCEE and MoE assess the project application on the basis of the criteria for DANCEE support and the national programmes and priorities. After the assessment, DANCEE may approve the application and award the project to the project holder by way of a grant.

Letter of grant

The rules of procedure for the award of contracts do not apply to the award of projects by application. Instead of a contract, a letter of grant is issued, within which terms and conditions are specified.

Statistical summary and data sheet

A statistical summary (and instructions for filling in this summary) and a data sheet are attached to the letter of grant. The data sheet must be filled in and submitted to DANCEE within four weeks of the receipt of the letter of grant.

The statistical summary must be filled in at the end of the project and submitted to DANCEE - please refer to Section 4.3.8.

## Award of Projects by Tender

A project by tender is initiated by DANCEE in cooperation with MoE, and DANCEE awards the project to a project holder in accordance with DEPA’s rules of procedure for award of contracts.

Standard contract form

The project is awarded by way of a contract, and DANCEE uses DEPA standard contract forms.

Statistical summary and data sheet

A statistical summary (and instructions for filling in this summary) and a data sheet are attached to the contract. The data sheet must be filled in and submitted to DANCEE within four weeks of the receipt of the contract.

The statistical summary must be filled in at the end of the project and submitted to DANCEE - please refer to Section 4.3.8.

The purpose of this section is to provide an overview of DEPA’s rules of procedure for the award of contracts and the standard contract forms used by DEPA. For a more comprehensive description of these tender and contract issues, see DEPA’s separate Manual for Tendering and Contracting, also mentioned in Section 3.3.4.

### Rules and Procedures for Award of Contracts

Governing rules and regulations

Normally, DEPA awards contracts under the DANCEE in pursuance of an international agreement between DEPA and a partner country which is not a member of the EU.

In such situations, the EU directives on public service contracts (92/50/EEC) and public supply contracts (93/36/EEC) do not apply to the award. Hence, DEPA’s award of contracts under the DANCEE programme is normally governed only by national rules. In this manual, procedures for award of contracts and thresholds for award procedures are based on national rules.

Project holders

DEPA requires the project holders to follow these rules of procedure when undertaking procurement as part of the services paid for by DANCEE funds.

Procedures for Award of Contracts

DEPA uses the following procedures for the award of contracts (in short “the award procedures”):

- direct award,

- negotiated procedure without publication of notice,

- open or restricted procedure with publication of notice.

Direct award

In a direct award, DEPA consults one company of DEPA’s choice and negotiates the terms of the contract with the company. Before deciding upon a particular company, DEPA may invite expressions of interest from companies.

Negotiated procedure

In a negotiated procedure without publication of notice, DEPA selects a smaller number of companies and invites each of them to submit a tender. DEPA may, prior to invitation, call for expressions of interest from companies.

Open procedure

In an open procedure with publication of notice, DEPA advertises the contract by publication of notice in which DEPA invites all interested companies to submit tenders.

Restricted procedure

In a restricted procedure with publication of notice, DEPA advertises the contract by publication of a notice in which DEPA invites requests for participation in the tender pre-qualification. Based upon a set of selection criteria, DEPA then selects a few companies to submit tenders. Only the prequalified companies are invited to submit tenders.

In all award procedures involving more than one tender, the contract is awarded after an evaluation of the tenders on the basis of the award criteria that are included in the tender documents issued by DEPA to the tenders.

Award procedure

In every award, DEPA will follow the award procedure which, in consideration of the particular circumstances, ensures the most economic and efficient outcome. Publication of notice is always required, if the value of the contract is estimated to equal or exceed the thresholds specified below under Thresholds for Award Procedures.

When a contract is awarded by a procedure with publication of notice, DEPA will normally follow the restricted procedure. DEPA will only follow the open procedure in particular cases where DEPA expects to receive only a small number of tenders due to the nature of the services or the supply and/or where DEPA wishes to save the time required for a pre-qualification.

The most common award procedure (restricted procedure with publication of notice) involves the following steps:

- publication of notice in Danish newspapers and/or professional journals of the opportunity for tendering,

- pre-qualification,

- invitation to tender and issuance of tender documents,

- receipt of tenders and evaluation,

- award of contract.

Thresholds for Award Procedures

Thresholds for award procedures

Contracts with a value (net of VAT) estimated to be below the threshold may be awarded by a procedure without publication of notice, whereas contracts with a value (net of VAT) estimated to equal or exceed the threshold shall be awarded by a procedure with publication of notice.

The thresholds for the different types of contract are specified in Table 3.1.

Table 3.1

|  | Estimated Value of Contract (Net of VAT) in DKK |
| --- | --- |
| Type of Contract | Procedure without publication of notice | Procedure with publication of notice |
| Service (1) | < 1.5 million | > 1.5 million |
| Supply (2) | < 1.0 million | > 1.0 million |
| Work | < 1.0 million | > 1.0 million |
| Mixed (3) | < 2.0 millions | > 2.0 million |

- The value of a service contract includes fees only and not reimbursable expenses or the value of supplies or works to be procured by a project holder as part of the services or which are arranged by other parties.

- For purposes of the threshold, the term “supply contract” covers not only contracts for the delivery of goods but also contracts for the delivery and installation of goods. Particular requirements apply to the number of bids to be solicited before the award of a supply contract without publication of notice.

- For purposes of the threshold, the term “mixed contract” means a contract with one company for a combination of services, supplies and /or works. The threshold for mixed contracts only applies if the values of the separate components of the contract do not exceed their individual thresholds. A contract providing for the procurement of supplies and/or works as part of the services is not a mixed contract as the project holder will not be the supplier or contractor.

No division of a contract

No contract shall be divided with the intent of reducing the value of the resulting contract(s) below these thresholds with the purpose of circumventing the rules.

Exemptions

DEPA may award a contract without publication of notice irrespective of the value of the contract by an exemption from the rules of procedure.

An exemption, however, shall be justified by particular circumstances, including reasons of extreme urgency or technical reasons for which the services or supplies may be provided or delivered only by a particular person or company. Further, an exemption requires the approval of DEPA’s management.

### Standard Contract Forms

In projects by tender DEPA will normally use standard contract forms.

The standard contract forms most frequently used by DEPA are the KR-contract form and the FIDIC contract forms.

KR-contract form

The KR-contract form is used for short term agreements on consultancy services. KR is an abbreviation of the Danish term “Korttidsrådgivning” which translates into “short term consultancy services”.

The KR-contract is governed by rules and guidelines for short-term agreements on supply of consultancy services (the KR-rules).

The KR-rules is an agreed document on which the Danish Ministry of Foreign Affairs and DEPA for the one part and the Danish Association of Consulting Engineers (“F.R.I.”) and other professional associations for the second part are in agreement.

The KR-rules only apply to service providers who are members of the associations which are party to the agreement on the KR-rules.

For practical reasons, DEPA may use the KR-contract form when contracting services from a service provider who is not a member of the above associations, but in that case DEPA reserves the right to deviate from the KR-rules.

Pursuant to the KR-rules, the KR-contract form can be used when

- the duration of the services does not exceed a period of one year, and

- the contract sum (fees and reimbursable expenses) does not exceed DKK 5.0 million

Normally, DEPA only uses the KR-contract form when the contract is awarded by a procedure without publication of notice (See Section 3.3.1).

FIDIC contract forms

“FIDIC” is the International Federation of Consulting Engineers.

FIDIC has published various contract forms, and where applicable, DEPA normally uses the FIDIC contract forms.

DEPA will use the particular FIDIC contract form which is the most appropriate in consideration of the nature of the contract. However, the White FIDIC (see footnote) is only used when the KR-contract form cannot be used.

Other contract forms

For the procurement of supplies, DEPA may use various contract forms which include World Bank and EU tendering and contract forms.

### Eligibility

General eligibility

In general, all persons and companies are eligible for the award of a contract by DEPA, and only a few restrictions apply.

The only general restriction on the eligibility is that DEPA will exclude from the award procedures any person or company who has unfulfilled obligations relating to the payment of taxes in excess of DKK 100,000. Reference is made to the Danish act on restrictions on debtors’ eligibility to participate in public tender procedures (Act no. 1093 of 21 December 1984).

Particular eligibility

To be eligible for the award of a particular contract, a person or company must comply with the necessary legal, technical and financial requirements and must have the capability and adequacy of resources to provide the particular deliverables effectively. In a negotiated procedure without publication and a restricted procedure with publication of notice, only the tenders selected or prequalified by DEPA are eligible to submit tenders.

Rules of equality of treatment of the tenders in a tender procedure exclude from participation any person or company who has an unfair competitive advantage.

An unfair competitive advantage may be gained from participation in the project phases preceding the tender. However, only previous participation which DEPA considers to result in an unfair competitive advantage will cause exclusion from tendering. In these decisions, DEPA follows the guidelines on the principle of the equality of treatment issued by the Danish Competition Agency (KonkurrenceStyrelsen).

On request, DEPA may render an advance opinion on the particular eligibility of a person or company before a tender procedure. Although any exclusion will be based upon an individual and concrete decision, participation in the project phase immediately preceding the tender will normally result in exclusion. An appraisal prior to the tender will normally be regarded as sufficient to clear a person or company from exclusion on the grounds of an unfair competitive advantage.

In order to avoid any doubt about eligibility, DEPA may require a person or a company to agree to waive participation in a subsequent tender on the same project.

### DEPA’s Manual for Tendering and Contracting

DEPA contracting manual

DEPA has issued a separate manual for the tendering and contracting of projects; this manual also applies to projects funded under the DANCEE.

The separate manual provides a detailed description of DEPA’s rules of procedure for award of contracts, standard contract forms and guidelines for various contract issues.

All detailed questions about tendering and contracting are referred to the separate manual.

# Project Implementation

## Key Stakeholders in Project Implementation

A number of stakeholders are involved in the implementation of projects. Key stakeholders responsible for project implementation are:

- project holder,

- beneficiary,

- MoE,

- DANCEE.

Key persons appointed by each key stakeholder are shown in Figure 4.1. Responsibilities and tasks of the key stakeholders and key persons are described in the following sections.

### The Project Holder

Responsibility of the project holder

Projects funded under the DANCEE cover a wide range of services, supplies and works, and the particular tasks and responsibilities of project holders vary correspondingly.

At one extreme, the implementation may rely almost entirely on the project holder; at another extreme, the beneficiary or other stakeholders may implement major parts of a project.

As a general rule, DEPA will hold a project holder responsible for the achievement of the immediate objectives of the project, but the particular capacity or role of the project holder as specified in the project document may modify this responsibility.

DANCEE’s prior or subsequent approval of proposals, initiatives and approaches does not limit the professional responsibility of the project holder in terms of the appropriateness or feasibility thereof, unless the project holder in advance explicitly has alerted DANCEE to particular risks associated therewith. This also applies to any information on the progress or quality of the implementation provided by the project holder to DANCEE in reports, etc.

Figure 4.1

Key Stakeholders

The project holder will assign a team of international and national experts to implement the project. The project holder will appoint a team leader and a project director. The project director will be responsible for quality assurance of the project implementation and project outputs. The team leader has the overall daily responsibility for the timely and correct implementation of the project. In most projects the project holder will also assign a local assistant team leader.

Team leader

DANCEE’s acceptance of the team leader - and of expatriate personnel in general - is part of the contract procedure and procedure for approval of applications. Technical, professional and personal qualifications and past experience and references of expatriate personnel will be evaluated by DANCEE.

The team leader is expected to establish a smooth working relationship with the local project manager, local consultants and other stakeholders. Further, the team leader will draft the specific work plans for all experts involved in the project and supervise the work performed.

The team leader will be responsible for organising a steering committee (SC) and - if agreed - also a advisory committee - please refer to Sections 4.2.2 and 4.2.3. The team leader will act as secretary to the steering committee and the possible advisory committee.

In particular, the team leader will ensure:

- assistance to the local project director in organising steering committee meetings,

- assistance to the local project manager in organising advisory committee meetings,

- development of the project procedures manual,

- supervision of the work of all expatriate staff and local sub-contractors,

- timely delivery of all goods and services at the project implementation site,

- drafting and submission of reports to the steering committee and DANCEE according to the project document,

- a positive and correct image of the project in the partner country,

- dissemination of project results.

### The Beneficiary

Responsibility

The beneficiary is the organisation in the partner country which benefits from the project and which receives the results of the project after completion. The beneficiary will normally implement local project components.

The beneficiary will have the overall responsibility for implementation of local project components. The responsibilities of the beneficiary will be clearly defined in the project document.

The beneficiary provides any local services agreed in the project document, and is responsible for the correct and timely service of all those local sub-contractors and local stakeholders which do not form a part of the project holder’s team.

A representative appointed by the beneficiary serves as deputy chairman of the steering committee and chairs all meetings of the advisory committee - please refer to Sections 4.2.2 and 4.2.3.

Local project manager

The beneficiary will nominate a local project manager who will have the day-to-day responsibility for the implementation of the local project component working in an informal project management group with the team leader.

### The Ministry of Environment

Responsibility of MoE

MoE has the overall local responsibility for the implementation of the country programme. In this capacity, MoE also has overall responsibility for monitoring the progress of project implementation and the project’s contribution to the overall country programme.

Local project director

MoE will appoint a local project director who will chair all steering committee meetings.

MoE has the right to demand a halt of a project if MoE deems that it is not progressing according to the project document or if external matters indicate a need for a reformulation of the project. However, such a request must be directed to DANCEE, as only DANCEE has the authority to demand that the project holder halts the implementation of the project according to the provisions in the contract or the letter of grant between DANCEE and the project holder. Likewise, if MoE requires changes in the project, the matter shall be discussed in the steering committee and any decision shall be agreed with DANCEE.

### DANCEE

Responsibility of the country coordinator

DANCEE has overall supervision responsibility for the projects. One country coordinator has been appointed to handle all relations with one specific partner country. This implies at least two annual meetings to negotiate and prioritise the project long-list into the project short-list and to assess ongoing and finalised projects. The overall responsibility for all projects in one individual partner country is undertaken by the relevant country coordinator. However, other DEPA specialists or specialists from other agencies within MoEE may be appointed to be responsible for a specific project.

The country coordinator will follow the progress of project implementation through the assessment of reports, accounting statements, reports from the LPC and by making site visits.

Local project coordinator

The LPC is a local native-speaking specialist employed by DANCEE and based in the partner country - most often in MoE. The main task is to assist the country coordinator in coordinating DANCEE activities in the partner country.

The LPC will monitor project implementation by visiting the project implementation sites regularly. Inadequate performance in relation to the project document will be reported to DANCEE. The project holder will then be contacted by DANCEE in order to find possible solutions to the problems incurred. The local project coordinator does not, however, have the authority to demand changes in project implementation.

DANCEE  can stop project implementation

If a project is not progressing according to plans in the project document, DANCEE reserves the right and authority to halt its implementation or terminate the project.

## Management Forums

To ensure the efficient implementation of projects, each DANCEE project will establish a management structure for project implementation. The type of management structure established will depend on the particular tasks of the project. The management structure will be described in the project document and will be elaborated in the procedures manual - please refer to Section 4.3.5.

### Project Management Group

Responsibilities

The team leader and the local project manager constitute the project management group. The project management group is responsible for the day-to-day implementation of the project.

The team leader is responsible on behalf of the project holder and the local project manager is responsible for inputs from the beneficiary.

The tasks and responsibilities of the team leader and the local project manager are described in the project document and shall be elaborated in the procedures manual.

### Steering Committee

For most projects, DANCEE recommends a steering committee. Some projects, e.g. projects which basically consist of equipment deliveries may not require a steering committee.

Established by Project Holder

It is the responsibility of the project holder to establish a steering committee in close collaboration with MoE and the beneficiary. No later than six weeks after the start of the project, the team leader shall submit a proposal to DANCEE on the proposed composition of the steering committee. DANCEE will approve or amend the proposal for composition of the steering committee within 10 working days of receipt of the proposal.

Members

Members of the steering committee shall include as a minimum:

- the local project director (chairman, appointed by MoE),

- a representative from the beneficiary (deputy chairman, appointed by the beneficiary),

- the project director (appointed by the project holder),

- a representative from MoEE (appointed by DANCEE),

- the local project manager (observer, appointed by the beneficiary),

- the team leader (observer and secretary, appointed by the project holder).

The steering committee may be expanded as appropriate to include:

- representatives of regional and local authorities,

- other ministries,

- private organisations,

- research and educational institutions,

- NGOs,

- representatives of other donors (in the case of co-financed projects).

Responsibility

The key responsibility of the steering committee is to monitor and supervise project implementation. This will be done by approving project reports, i.e. the inception report, the progress reports and the final report. This implies that the steering committee should have four yearly meetings as the progress reports are submitted quarterly by the project holder.

First steering committee meeting

The project holder will call the first meeting of the steering committee no later than three months after the start of the project. Generally, the first meeting of the steering committee shall be used for the formal introduction of  project stakeholders. The team leader will present the first detailed plan for project implementation and introduce his team. At its first meeting the steering committee will approve or request revision of  the inception report - please refer to Section 4.3.4. Recommended guidelines for steering committee meetings are shown in Enclosure E.

Final steering committee meeting

The focus of the final steering committee meeting will be an assessment of whether project objectives have been achieved. The committee will respond to a detailed reading of the completion report - please refer to Section 4.3.7. The conclusions of discussions will be summarised in the minutes of meetings. The minutes will be forwarded to DANCEE.

Project sustainability

Throughout the project period significant attention should be paid to the future. The team leader should monitor the end-of-project situation and the status of the sustainability of the project. This may also include a consideration of additional tasks deemed necessary to enhance the sustainability of the project’s results which are beyond the scope of the project document. At the final steering committee meeting, the team leader should give a presentation on the end-of-project situation. Particular focus will be on the beneficiary’s responsibility for developing the results achieved. Recommendations for locally initiated follow-up activities will be highlighted.

Costs of steering committee meetings

The project budget will have a provision to meet the costs of steering committee meetings.

### Advisory Committee

The MoE and the beneficiary may decide to establish a project advisory committee to follow the development of the project implementation. Members of a project advisory committee will typically represent local and regional authorities, organisations, educational institutions, research institutes, NGOs, independent experts, citizen’s groups and other stakeholders. A representative appointed by the beneficiary chairs all meetings of the advisory committee.

No formal responsibilities

This committee has no formal responsibility for project implementation. It decides its own order of business and frequency of meetings (twice a year may be regarded as a minimum). The committee can only give advice. This advice will be channelled to the steering committee by the chairman.

The project budget may have a small provision for to meet the costs of advisory meetings.

## Project Monitoring and Reporting

### Project Monitoring Systems

Monitoring system

Project monitoring systems are established to ensure that data are available for both the monitoring of the project implementation and the evaluation of the project’s impact, sustainability and relevance.

Each DANCEE supported project is required to establish a monitoring system at the start of the project. The aims of the monitoring system are:

- to identify problems during project implementation and to ensure that timely action is taken to solve the problems,

- to improve the quality of future support based on an analysis of lessons learned.

Issues to be monitored

In Table 4.1 below the issues to be monitored are listed in accordance with the project logic.

Table 4.1:

Issues to be monitored

| The Project Logic | Project Progress | Project Impact/Effectiveness |  |
| --- | --- | --- | --- |
| Development Objective |  | Project impact |  |
| Immediate Objective |  | Effectiveness in project implementation Sustainability of project results |  |
| Outputs | Extent of achievement of results | Sustainability of project activities |  |
| Activities | Activities carried out according to plans | Efficiency of activities |  |
| Inputs | Inputs delivered according to plans |  |  |
| Assumptions | Changes in the environment |  |  |

Progress monitoring

Monitoring is the continuous and periodic assessment of the physical implementation of a project. Monitoring is carried out by the project management group. Project monitoring shall assess if inputs have been delivered and activities carried out according to plans, and if the project has achieved its outputs. Monitoring also involves an assessment of the likelihood of achieving the project objectives. No projects can be implemented in isolation from the surrounding environment and, therefore, changes in the project’s social and economic environment shall also be assessed. The efficiency shall be monitored by assessing the “productivity” of the implementation process - how economically inputs are transformed into outputs.

Evaluation

Part of the project evaluation will be the responsibility of the project holder and should be reported to DANCEE in the completion report and the statistical summary. Additionally, DANCEE may decide to carry out an independant evaluation - please refer to Section 5.

The effectiveness of the project is judged by an assessment of the extent to which the project has achieved its immediate objectives. The foreseen and unforeseen consequences of a project, to the beneficiary in particular, and to society in general, shall be assessed.

The project’s effectiveness and impacts shall be assessed by the project holder as part of the completion report. In addition, DANCEE can decide that the project should undergo an external evaluation according to the guidelines in Section 5.

The monitoring system should normally ensure that baseline data are available against which to assess the environmental impact of a project.

Baseline measurements or estimates should be made both before and after project implementation in order to measure the environmental impacts of the project - please refer to Section 4.3.3.

Indicators

Monitoring will normally be based on indicators. Indicators are established as success criteria at the output and objective level. Indicators are used as an economic and efficient way of making a partial test, on the premise that if the test conditions have been fulfilled, then the project’s outputs and objectives have also been fulfilled.

An indicator should be:

- substantial in relation to the specific outputs and objectives it measures, in terms of quantity, quality, time, location and target groups;,

- factual rather than subjective,

- plausible (the changes recorded should be directly attributed to the indicator),

- based on obtainable data, preferably existing data.

The list of indicators used by DANCEE as part of the statistical summary is provided in Enclosure H.

Some examples of typical indicators are:

- increase in available volume at sanitary landfills,

- number of hectares turned into natural park land,

- energy savings,

- sulphur reductions.

Milestones

The implementation of activities is monitored by a comparison with milestones established in the project’s work plan. A milestone indicates when a given set of activities is expected to have been performed.

Specifying indicators and milestones

Indicators and milestones are normally defined during the project’s inception period, as the project document will often only describe indicators and milestones for project monitoring in general terms.  Indicators and milestones should be established in collaboration with local partners and the beneficiary, to ensure that all parties to the project are committed to the achievement of the project’s outputs and objectives from the beginning.

### Reporting

During project implementation, the project holder is responsible for the production of the reports specified in the project document. Reports normally include monitoring reports, management reports and technical reports. The different reports to be presented by the project holder are outlined in Figure 4.2.

Figure 4.2

Reports produced during project implementation

The procedures manual

Management reports include:

- a procedures manual setting out the management procedures including the monitoring system.

Technical reports

Technical reports may include:

- masterplans,

- feasibility studies,

- manuals,

- tender documents.

Reporting monitoring results

The outcomes of project monitoring are reported by the project management group to the steering committee and to DANCEE. The focus of project monitoring will initially be on the delivery of inputs and the implementation of activities, but as the project progresses, the monitoring emphasis will shift towards an assessment of achieved results.

The project reporting system is based on three types of monitoring reports:

- an inception report describing how the project is to be implemented in relation to the project document,

- progress reports which address project progress will normally be submitted quarterly. The progress reports should be brief, and focus on problems and deviations, not repeating issues previously reported. Approved progress reports are a precondition for the settlement of invoices,

- a completion report summarising overall project achievements,

In addition to the above monitoring reports, a baseline study/description should be part of the project’s monitoring and evaluation system.

Formats and requirements for the individual reports are outlined below.

### Baseline Descriptions

A baseline description is established with the aim of describing the existing situation (the baseline) against which the impact of a project can be measured.

DANCEE  requires baseline descriptions

All DANCEE supported projects shall establish baseline descriptions.  
A baseline may refer to water quality parameters, biological diversity and species composition, the state of ecosystems, the physical background sustaining existing ecosystems or a specific species. Any impacts introduced as a change in the physical background shall be subsequently described and assessed in relation to a baseline description.

Two examples of baseline descriptions are given below.

Baseline for waste water treatment

For projects related to waste water treatment the baseline description will be used for the evaluation of the treatment facilities and the pollution of the receiving waters. The amount of waste water discharged will be assessed together with the content of the polluting substances (especially BOD, nitrogen, ammonia and phosphorous). If the catchment area includes large industries, the discharge of heavy metals, petro-chemical by-products etc. will be assessed.

Existing waste water treatment facilities will be evaluated and a baseline describing the present treatment facilities, their efficiency and the level of pollution from the discharge of waste water will be established.

Next, an assessment will be made of the improvements in the waste water treatment required to meet an outlet quality equal to e.g. EU standards and the expected consequent effect on the receiving waters.

In some projects, it is not possible to measure the direct impact of the project on the environment. In these situations, the baseline can be established by a comparison with the pre-existing processes. Two examples are given below of baseline studies for projects with no direct, measurable environmental impacts.

Baselines for legislative assistance

For assistance related to environmental legislation, baseline descriptions usually consist of a description of existing national legislation. In accession projects, legislative gap analysis is the usual methodology, i.e. a comparison of national legislation with the requirements found in EU Directives. The legislative baseline refers methodologically to provisions found in the national legislation. Required changes are defined by EU requirements.

Baselines for technical studies

For technical studies, baseline descriptions are used for an evaluation of the required enhancements in the technical production capabilities of enterprises, or of their capability to prevent pollution of the external environment.

An example of such evaluations is related to the Integrated Pollution Prevention Control (IPPC) Directive in European countries. From an evaluation of existing production facilities in industrial units, a baseline describing production facilities and levels of pollution control is established. Next, an assessment is made of modified production capability and pollution prevention measures based on the introduction of Best Available Technology (BAT), also in accordance with the IPPC Directive. All achievements are described in relation to the baseline situation.

### Approval of Reports

Reports need to be approved first by the steering committee and subsequently by DANCEE. The general procedures for the approval of project reports are described below.

The steering committee

The steering committee may reject a report if it is of poor quality, i.e. if it does not comply with DANCEE’s requirements or if it does not give a fair assessment of the project implementation. If a report indicates that project implementation is not meeting the expectations laid down in the project document and the proposed solutions seem inadequate, the report will normally be rejected.

Rejections of reports

If the steering committee rejects a report, the project holder will revise the report and re-submit it to the steering committee for their written approval. If members have not commented on the report within 10 working days, the report is deemed to be approved and can be forwarded to DANCEE by the team leader. If the steering committee again rejects the report, a further meeting will be called for approval of the report.

The project holder may request the chairman to ask the MoEE representative to participate in this further meeting, whether or not the MoEE representative took part in the meeting which rejected the original report. Once such a request has been submitted, the meeting cannot be held without the MoEE representative being present.

In those cases where the MoEE representative participates in the steering committee meetings, all reports are approved if the MoEE representative has no objections.

DANCEE’s approval of reports

DANCEE will normally approve reports at the recommendation of the steering committee. However, DANCEE may reject reports approved by the steering committee. If this happens, a further steering committee meeting will be convened and the MoEE representative must participate and provide reasons for the rejection of the report.

DANCEE’s approval of reports does not limit the professional responsibilities of the project holder - please refer to Section 4.1.1.

### Inception Report

Typically all tendered projects have an inception phase and an inception report, whereas some projects by application, and most equipment supply projects do not have an inception phase. The project document will specify whether the project requires an inception phase. The usual length of the inception phase is three months.

Inception phase

The inception report will include:

- the revised project document (or an addendum to the original project document),

- the revised project implementation plan,

- the revised project budget.

The procedures manual and the baseline study will be attached to the inception report. The draft inception report shall normally be submitted to the steering committee and DANCEE at least one month before the first steering committee meeting.

Assessment of project document

During the inception phase, and at the team leader’s initiative, the project management group will assess the project document, the budget and the plan of implementation. They will detail project activities and make required adjustments according to changes in the local environment. They will specify the project implementation plan. The project implementation plan will indicate when draft monitoring reports will be forwarded to the steering committee and to DANCEE. If any deficiencies or need for modifications are found, this must be clarified and agreed, and appropriate action taken.

The assessment of the project document is intended to verify that the description of the context, problems and assumptions for the project remain valid. In addition, the adequacy of inputs and support from the implementing organisation and other parties will be assessed, and clear roles and responsibilities will be defined. The assessment will also verify that the outputs can be produced with the planned activities and inputs specified in the project implementation plan. The indicators and means of verification will be detailed and refined, and the adequacy of baseline data will be checked.

Adjustments to project document

The results of this assessment will be documented in the inception report as shown in Table 4.2. If adjustments are required to the project document, the project holder must submit to DANCEE a revised project document or an addendum to the existing project document. DANCEE must approve the adjustments by co-signing with the project holder the revised project document or addendum to the existing project document.

Approval of inception report

Comments by the steering committee to the inception report shall be submitted to DANCEE by the project holder. DANCEE shall approve the report in writing within ten working days of receipt of the comments. If DANCEE cannot approve the report within ten working days of receipt of the comments from the steering committee, notice shall be given in writing to the project holder.

Table 4.2:

Inception Report Format

Table of contents

- Cover sheet

- Map of location

- List of abbreviations

- Executive summary

1.		Project context and review of assumptions

2. 	Proposal for changes (project interventions)

2.1. 	Development objective with indicators

2.2.	Immediate objective with indicators

2.3.	Outputs with indicators

2.4.	Main activities with indicators

2.5.	Inputs

2.6	Assumptions, risks and preconditions

3.		Comments and/or revisions (if any) to project implementation plan

4.		Comments and/or revisions (if any) to the project document

Annexes

- Revised project document

- Revised project implementation plan/time schedule

- Revised budget

- Revised list of addresses

### Procedures Manual

The procedures manual serves as a guide for project staff, sub-consultants, steering committee members and other stakeholders. It contains information on project organisation and procedures and responsibilities for general management, financial management, project monitoring and reporting, and quality management.

Monitoring

The monitoring procedures shall clearly indicate:

- the indicators and milestones to be monitored,

- how data will be compiled,

- persons responsible for compiling the data and reporting problems,

- persons responsible for remedial actions.

Table 4.3:

Procedures Manual Format (example)

Table of contents

- Cover sheet

- Project organisation, institutional relationships and responsibilities: Distribution of responsibilities among the beneficiary organisation, MoE, DEPA, country coordinator, project management group and staff, steering committee, external parties, and other stake-holders.

- Lines of communication: procedures for communication among the beneficiary organisation, MoE, country coordinator, project management group and staff , steering committee, external parties, and other stake-holders.

- System and procedures for filing and documentation.

- Staff rules: provisions regarding working hours, field trips, leave, etc. for national and international project staff.

- Project monitoring: management procedures for project monitoring, including the establishment of baseline data and indicators for project monitoring and evaluation.

- Financial procedures: procedures and responsibilities should be defined in relation to the following matters: (i) preparation and approval of internal budgets; (ii) approval of expenditures; (iii) payment of bills and collection of receipts, and (iv) handling of cash.

- Project assets: inventory, control, and use of project assets, including vehicles, equipment, facilities, etc.

- Quality assurance: procedures and plans for assuring the quality of project outputs, including reports and other documents.

Format of manual

Table 4.3 suggests contents and format for a procedures manual, but a manual will always be project-specific. Thus, it may contain additional information that project staff and steering committee may find appropriate. The physical format should be flexible (ring binder as well as electronic format) to allow continuous updating during the project’s lifetime.

### Progress Reports

Progress reports are prepared by the project management group at the initiative of the team leader. They are normally submitted to DANCEE and the steering committee every three months. The scheduling of progress reports is established in the inception report, and progress reports should to the extent possible correspond to the planned achievement of project outputs.

Means of communication

The progress reports (max. 10 pages plus annexes) are a means for the project management group to communicate information about the implementation of the project to the steering committee, MoE, DANCEE and other stakeholders.

Focus on problems

Progress reports should not repeat information contained in previously submitted reports. Their prime function is to point to unexpected problems which have occurred in the reporting period or which can be foreseen. Progress reports should propose solutions to identified problems for approval by the steering committee and DANCEE. These reports will also allow controlled adjustments, convey information to stakeholders, and serve as a project diary, showing agreed alterations to the project document.

DANCEE will primarily use the progress reports to monitor project implementation and will not normally initiate action unless specifically requested by the team leader or by MoE, or in cases where it is obvious that project implementation is not progressing satisfactory.

Approval of progress report

The draft progress report is normally submitted to the steering committee and DANCEE at least ten working days before the steering committee meeting. The steering committee comments on the draft progress report which is submitted to DANCEE after the meeting. DANCEE shall approve the report in writing within ten working days upon receipt of comments from the steering committee. If DANCEE cannot approve within ten working days, notice shall be given in writing to the project holder.

Approval of changes

If changes to the project outputs or objectives become necessary, these will be presented and documented in the progress reports. Proposed changes should be listed in the covering letter to the progress report for subsequent approval by DANCEE. Adjustments will be approved only when the covering letter is signed by DANCEE and the project holder - please refer to Enclosure F.

Adjustments of budget lines

Adjustments of budget lines are possible to a limited extent in tendered projects - please refer to Section 4.4. For projects by application, adjustment of budget lines is only possible to a limited extent and only after DANCEE’s approval. Accounts for reimbursable expenses and accounts for fees should be submitted at the same time as progress reports. Payments cannot be made without approval of submitted progress reports.

A suggested format for progress reports is shown in Table 4.4. However, the reports may contain additional information found appropriate by the project management group.

Table 4.4:

Progress Report Format

Covering letter, please refer to Enclosure F

Table of contents

- Cover sheet

- Executive summary

- Project context: review of project assumptions in the light of any new problems or opportunities.

- Project outputs: review of project outputs and Indicators achieved and/or due during the reporting period.

- Project activities: review of implementation of activities according to plan.

- Project inputs: review of project inputs used during the reporting period.

- Financial statement: overview of the financial situation of the project compared to the budget, and requests for budget changes (if any).

- Project implementation status: problems and opportunities (if any) encountered during the reporting period not covered elsewhere in the report, such as:

(a) analysis of possible unintended impacts and suggestions for action;

(b) review of likelihood of achievement of project objectives;

(c) review of overall project strategy; and (d) analysis of project sustainability.

- Revisions to project implementation plan (PIP)  or project document (if any).

Annexes

- Financial statement (see Table 4.6 below)

- Adjustments to project implementation plan (if appropriate)

- Amendments to the document (if appropriate)

### Technical Reports

Technical reports may include masterplans, feasibility studies, manuals, tender documents etc.

The technical reports can be used as milestones and it must be specified in the project document which technical reports are required.

The technical reports must be submitted to DANCEE in accordance with the time scedule in the project document. DANCEE shall approve the report within 20 working days upon reception. This approval must be in written form and addressed to the project holder.

### Completion Report

At the initiative and responsibility of the team leader, the team leader and the local project manager will prepare a draft completion report prior to the end of the project. The primary purposes of the report are:

- to document the status of the project at the time of completion, i.e. to what extent the outputs have been produced and the objectives achieved, or are likely to be achieved,

- to provide an assessment of the need for possible further assistance from DANCEE or other sources,

- to contribute to the accumulation and dissemination of experience,

- to provide a basis for evaluation.

The team leader will submit the draft completion report to the steering committee. The steering committee will discuss the draft completion report. The draft completion report will be sent to DANCEE in two copies after approval by the steering committee.

Approval of completion report

The draft completion report is normally submitted to the steering committee and DANCEE at least one month before the steering committee meeting. After the steering committee, comments are submitted to DANCEE. DANCEE shall approve the report in writing within 20 working days upon receipt of the comments. If DANCEE cannot approve the report within 20 working days upon receipt of the comments from the SC, notice will be given in writing to the project holder.

Final completion report

If there is no request for changes, the draft completion report will become final by a replacement of the cover page. If the steering committee or DANCEE request changes, a revised draft completion report will be submitted by the team leader to the chairman of the steering committee and to DANCEE within 10 working days of receipt of the steering committee’s or DANCEE’s comments. If the project holder does not receive any comments from the steering committee or DANCEE within 20 working days, the revised draft completion report may be considered approved.

Statistical summary

DANCEE maintains a database of all projects carried out under the DANCEE programme. This database contains e.g. information on environmental impacts, ex-post summary, co-financing. All DANCEE projects must be included in this database. For this purpose, a statistical summary for each project must be filled in.

The project holder is responsible for filling in the data necessary in the statistal summary at the end of the project. The project holder shall submit the statistical summary (in MS Word format) together with the completion report. The summary must be filled in in accordance to specific instructions and submitted to DANCEE on diskette.

With the approval of the completion report and the statistical summary, the project holder may submit his final accounts and invoice.

The project holder will have completed his services once the completion report, the statistical summary and the final accounts have been accepted by DANCEE.

A format for the completion report is shown in Table 4.5.

Table 4.5

Completion Report Format

Table of contents

- Cover sheet

- Map of location

- List of abbreviations

- Executive summary

- Introduction: brief description of the project and its background.

- Project context: review of project assumptions and any alternative opportunities

- Project outputs: review of all project outputs

- Project inputs: review of all project inputs, including international and national staff inputs, equipment, facilities, etc.

- Financial statement: overview of the financial situation of the project compared to the budget at the time of project start. Complete audited accounts must also be included.

- Project sustainability: assessment of sustainability.

- Impact assessment: preliminary evaluation of project effectiveness in achieving its o.Objectives and of any unintended impacts.

- Recommendations: summary of recommended follow-up actions by the project holder, the beneficiary, MoE and by DEPA (including recommendations for a formal, independent project evaluation, if appropriate).

- Lessons learned: summary of experience that may be of general interest, and of any achievements or obstacles that have not been described above, including an assessment of overall project strategy.

Annexes

- Financial statement (see Table 4.6)

- Procurement summary

- Amendments to the project document (if appropriate)

- List of reports and other documents produced by the project

## Financial Management

The purpose of this Section is to provide an overview of DANCEE’s terms of payment and requirements for financial reporting. It is for information only, has no legal status, and can be deviated from by the DANCEE. The legal and detailed terms and requirements for a specific project are specified in the contracts and the letter of grant.

### Financial Management

Project holder’s responsibility

The general responsibility for the financial management of funds provided by DANCEE to projects rests with the project holder.

Financial management responsibilities entail inter alia that all fees and reimbursable expenses invoiced to DANCEE are against specific provisions in the budget and are adequately supported by evidence that procurement is based upon fair and open bargaining or tendering and on competitive terms and conditions, and that the use of the funds is appropriately accounted for. In general, financial management must be in accordance with common professional principles of sound commercial practice.

DANCEE cannot accept that any offer, payment, consideration, or benefit of any kind, which constitutes an illegal or corrupt practice, shall be made or accepted, directly or indirectly, as an inducement or reward in relation to the tendering, award, execution or performance of a contract or a grant. Any such practice will be grounds for the immediate termination of a project. The project holder will be permanently disqualified from DANCEE funded projects and activities. DANCEE may also pursue further civil and criminal actions against the project holder.

### Payment Schemes

DANCEE will pay the project holder for fees and reimbursable expenses which are specified in the budget and incurred in the implementation of the project within the budgeted amounts.

Payments will be made on the basis of invoices submitted to DANCEE by the project holder.

Projects by Tender

Advance payment

In projects by tender, DANCEE may make advance payments to the project holder upon signing of the contract in an amount corresponding to a maximum of 30 % of the total estimated fees and to a maximum of 40 % of the total estimated reimbursable expenses. An advance payment must be repaid by means of pro rata deductions from the subsequent progress payments to the project holder.

Project holders other than NGOs must provide a security (bank guarantee) for an advance payment. For advance payments of less than DKK 400,000, DANCEE may waive this requirement.

DEPA may conduct an assessment of the institutional and financial standing of a NGO for purposes of determining the size of the advance payments.

Progress payments

Progress payments are made quarterly. DANCEE’s approval of the most recent progress report is a precondition for the progress payment.

Progress payments are made on the basis of invoices submitted to DANCEE by the project holder for the services rendered and for the reimbursable expenses actually incurred in the preceding quarter.

Final payment

In a KR-contract, the advance and progress payment can as a maximum amount to 75% of the total estimated fees and reimbursable expenses. A final payment is made after DANCEE’s approval of the final accounts.

For the procurement of supplies and works, DANCEE and the project holder may agree that DANCEE pays directly to the supplier or contractor on the basis of invoices endorsed for payment by the project holder.

Projects by Application

In projects by application, DANCEE will disburse the grant in two instalments.

First instalment

The first instalment corresponding to 90% of the grant will be paid at the time of submission of the completion report. If DANCEE at this point of time should have any substantial objections to making the payment, DANCEE may postpone it until DANCEE has approved the completion report and the audited final statement of accounts.

Second instalment

The second instalment (10% of the grant) will be paid when DANCEE has approved the completion report and the audited final statement of accounts.

The project holder shall submit invoices for the payment of the instalments.

Quarterly payments in projects longer than 6 months

In projects with a duration of more than 6 months, DANCEE may agree to make payments on account at quarterly intervals in amounts which correspond to fees and reimbursable expenses accrued in the preceding quarter. These payments cannot in total exceed 90% of the grant. Payments on account will not be finalised until DANCEE has approved the completion report and the audited final statement of accounts.

Advance payments to NGOs

Advance payments to NGOs are made in amounts which are suited to the accrual of fees and reimbursable expenses. Normally, DANCEE makes quarterly or biannual advance payments in amounts which correspond to the budgeted fees and reimbursable expenses in the following period.

DEPA may conduct an assessment of the institutional and financial standing of a NGO for purposes of determining the size of the advance payments.

Advance payment for supplies and works

Advance payments in connection with the procurement of supplies or works may correspond to maximum 75% of the costs. Such advance payments are subject to separate agreement between DANCEE and the project holder.

Project holders other than NGOs must provide a security (bank guarantee) for an advance payment. For advance payments of less than DKK 400,000 DEPA may waive this requirement.

Direct payment to supplier or contractor

For the procurement of supplies and works, DANCEE and the project holder may agree that DANCEE pays directly to the supplier or contractor on the basis of invoices endorsed for payment by the project holder.

### Terms of Payment

DANCEE will pay the invoices within a period of 30 days from receipt provided that the invoices are complete and not disputed and that the project holder has submitted requisite reports.

Payment of the invoice as of 31 December and the final invoice further require the submission of the annual or final statement of accounts.

VAT and Taxation

In a project by application, the grant is not subject to Danish VAT, but the grant is taxable income for the project holder.

Services, supplies and works under a contract with a Danish project holder or subcontractor are not subject to Danish VAT, if the deliverables exclusively are used outside the EU.

All funds from the DANCEE shall be exempted from VAT, duties and taxation in the partner country.

### Financial reporting

Statements of account

DANCEE may require that the project holder submits audited annual and final statements of accounts to DANCEE within a period of three months after December 31 or after completion.

In projects by application, the requirement for annual statements of accounts only applies if DANCEE has agreed to make payments on account.

For longer projects, the first annual statement of accounts and the final statement of accounts may cover a period of up to 14 months, and the consultant needs not submit annual statements of accounts within that period. The consultant shall in advance notify DANCEE of the omission of an annual statement of accounts.

The annual statement of accounts shall include a budget for the remaining project period.

The statements of accounts shall be in accordance with the specifications issued and be in the form which DANCEE may require at any time. Please refer to Table 4.6.

Audits

The annual and final statements of accounts shall be audited, and the auditor shall render his opinion and sign the statements.

The auditor shall be a state authorised or registered accountant.

The audit shall be conducted in accordance with standard auditing practice and any particular instructions issued by DANCEE.

The costs of the audits may be included in the budget as a reimbursable expense and invoiced to DANCEE.

Other donors

In case of projects which have been co-financed by funds from DANCEE and funds from other donors or financial institutions, DANCEE shall receive a copy of the auditing report from the entire project.

Inspection

DANCEE and its representatives shall be entitled to inspect and otherwise examine the project, including (but not limited to) all and any accounts, receipts, vouchers, contracts, and make site inspections, during and after the project. The project holder and the beneficiary are required to grant access for such inspection and examination. This also applies to investigations conducted by the office of the Auditor General of Denmark.

Table 4.6

Annual State of Accounts Format

Reporting Period:

Thousands of Danish Kroner

| Budget Line | Description | A Budgeted Amount (pro.doc.) | B Total in Previous Periods | C Expendi-ture in Current Period | D Budget for remaining project period | A-(B+C) Balance Remaining | % Remaining |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Fees |  |  |  |  |  |  |  |
|  | 1. |  |  |  |  |  |  |
|  | 2. |  |  |  |  |  |  |
|  | 3. |  |  |  |  |  |  |
|  | Sub-total |  |  |  |  |  |  |
| Reimbursables |  |  |  |  |  |  |  |
|  | 1. |  |  |  |  |  |  |
|  | 2. |  |  |  |  |  |  |
|  | 3. |  |  |  |  |  |  |
|  | Sub-total |  |  |  |  |  |  |
| Equipment |  |  |  |  |  |  |  |
|  | 1. |  |  |  |  |  |  |
|  | 2. |  |  |  |  |  |  |
|  | 3. |  |  |  |  |  |  |
|  | Sub-total |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |
| Contingency |  |  |  |  |  |  |  |
| Grand Total (incl contingency) |  |  |  |  |  |  |  |

# Evaluation

Evaluation

Evaluation is a systematic and objective assessment of the design, implementation and results of an on-going or completed project or programme. The aim of the evaluation is to determine the efficiency, effectiveness, impact, sustainability and relevance of the project. Evaluations are undertaken at the initiative of DANCEE.

The evaluations of DANCEE supported projects serve two purposes:

- To improve the quality of DANCEE support through better knowledge of the content and consequences of projects;

- To document the results to the political authorities and the general public.

Reviews

Reviews are midway between monitoring and evaluation, as they involve a fresh look at the objectives, design and performance of a project. Compared to evaluations, reviews are more limited in scope, time and focus. Reviews are used to verify the relevance and efficiency of the project. The focus of the review is in particular on any needs for adjustments of the project. Reviews are also carried out at the initiative of DANCEE.

The term “evaluation” is used below, when speaking of reviews and evaluations.

## Framework for Evaluation

Evaluation procedures

DANCEE applies the same evaluation procedures for tender and application projects. DANCEE operates with the three types of evaluations shown in Table 5.1 below.

Table 5.1:

Structure for Project Evaluation

| Type of Evaluation | Timing | Focus |
| --- | --- | --- |
| Mid-term Review | Mid-term | The project’s relevance Efficiency of activities The project’s effect The project’s impact |
| End-of-Project Evaluation | Last project year | The project’s effect The project’s impact Sustainability of project interventions |
| Ex-post Evaluation | 2 - 5 years after completion | Sustainability of project interventions |

Mid-term reviews

Mid-term reviews are carried out on projects with a duration of more than three years, on complicated and complex projects and on projects where problems have been identified. Mid-term reviews are carried out by a team of external consultants appointed by DANCEE. The mid-term review will verify the relevance, sustainability and efficiency of the project and will recommend relevant adjustments.

End-of-project evaluations

End-of-project evaluations will as a minimum be carried out as a desk evaluation by the MoEE representative. End-of-project evaluations may also be carried out by a team of external consultants appointed by DANCEE. The aim of the end-of-project evaluation is to assess what lasting impact the project is likely to have. The focus of the end-of-project evaluation is on the effectiveness of the project and the impact of the project. Furthermore, the end-of-project evaluation will assess the sustainability of the project.

Ex-post evaluation

DANCEE will normally carry out ex-post evaluations of groups of projects. The ex-post evaluation will focus on the sustainability of the projects’ impacts. Ex-post evaluations will be carried out by a team of external consultants appointed by DANCEE, 2-5 years after project completion.

Furthermore, DANCEE and its representatives are entitled to carry out inspections and examinations of projects, as described in Section 5.4.

## Evaluations Carried Out by External Consultants

### Terms of Reference

ToR

ToR for reviews and evaluations carried out by external consultants are developed by DANCEE. The ToR defines the objectives of the evaluation and indicates the issues which DANCEE finds of particular importance. In addition, information is provided on the background for the evaluation, the composition of the evaluation team and the timing of the evaluation. A standard outline of the DANCEE ToR is shown in Table 5.2.

### Contracting

The evaluation team

An external review or evaluation team will consist of 1-4 persons. The team can include both international consultants and consultants from the partner country, all the members being selected for their technical expertise. The team will present their independent views on the project.

The beneficiary

A representative from the beneficiary will act as a resource person for the evaluation team and will ensure that lessons learned are discussed with the beneficiary.

The team leader

DANCEE will sign a contract with the evaluation team. The ToR forms part of the contract. The contract will specify the team leader of the evaluation. The team leader will be responsible for the implementation of the evaluation and for the final reporting.

DANCEE will hold a briefing meeting with the team. The purpose of the meeting is to ensure that the team has the broad understanding of the project to be evaluated, to identify needs for further documentation and to discuss the ToR.

### Implementing the Evaluation

The evaluation team

The evaluation team is responsible for planning and undertaking the evaluation. The team leader will be responsible to DANCEE but will delegate assignments to the team members. The local project coordinator will upon request assist with the planning of a programme, visits and meetings for the evaluation team.

Local project

coordinator

Upon arrival in the partner country the team will consult with the local project coordinator and will brief MoE on the programme for the evaluation.

Table 5.2:

Standard Outline of DANCEE’s ToR for evaluations

| Main Elements in the ToR |
| --- |
| Project background | Project context and rationale Brief description of the project logic (the objectives and outputs of the project LFA) |
| Objective of the evaluation | Reasons related to formal decisions Reasons related to project performance The intended use of results |
| Scope and methods | The scope of the evaluation The type of analysis and method to be used and the degree of detail |
| Issues to be covered | Extent to which all or only selected areas of analysis and issues are to be covered (efficiency, effectiveness, impact, relevance and sustainability) Extent of specialisation |
| Evaluation team | Number of team members and their roles Required professional background and experience |
| Timetable | Approximate dates and allocation of time prior to, during and after the field work |
| Consultations in the field | Authorities, institutions and groups to be consulted during and at the end of the field work |
| Reporting | Deadlines for draft and final reports Specification of technical standards for final report |
| Documentation | Project document Project reports Relevant background reports |

Debriefing note

Before departure from the partner country, the team will debrief MoE. The head of the evaluation team will present a debriefing note to MoE. This note will form the basis for a discussion with MoE, the beneficiary and other stakeholders about the results of the evaluation.

The debriefing note should not exceed ten pages and will specify the findings and recommendations of the evaluation team. An outline for a debriefing note is shown in Figure 5.1 below.

Figure 5.1

Outline of debriefing note

Date and place of meeting Team composition

Introduction: the objective of the evaluation the scope of the evaluation

Activities undertaken

Key findings: relevance sustainability impact on environment effect efficiency

Recommendations

Assumptions

### The Evaluation Report

The evaluation team will write its evaluation report based on the findings and recommendations outlined in the debriefing note. The team will prepare a draft final report, which will be scrutinised by DANCEE before the final report is produced. The final report should not exceed 50 pages.

The format of the evaluation report is outlined in Table 5.3. The importance accorded to each of the points should reflect the ToR. The report will focus on the achievements of the project.

The evaluation team will comment on positive and negative aspects of the project, conclusions being operational and action-oriented.

DANCEE shall approve the draft evaluation report in writing to the team leader within 20 working days after reciving the draft.

## Lessons Learned

The application of the evaluation results

One of the main purposes of carrying out an evaluation is to applicate the evaluation results and lessons learned to new projects.

In the case of a mid-term review, the final evaluation report is given to the steering committee. The steering committee will review, approve or disapprove, and implement recommendations. DANCEE is responsible for submitting the final evaluation report to the project holder and the steering committee.

Final or ex-post evaluation

In an end-of-project or ex-post evaluation, the emphasis is on lessons learned for new projects and for future strategies. End-of-project evaluations will be discussed at the final steering committee meeting. The steering committee will discuss the lessons learned and will suggest adjustments to the beneficiary to ensure sustainability of project results. DANCEE and MoE will discuss the outcomes of ex-post evaluations with relevant stakeholders.

## Inspection and Examination of Projects

DANCEE and its representatives shall be entitled to inspect and otherwise examine projects, including (but not limited to) all and any accounts, receipts, contracts, and to make on-site inspections, during and after completion of the project. The project holder and the beneficiary are required to grant access and render the assistance necessary for such inspection and examination.

These provisions also apply to investigations conducted by the Office of the Auditor General of Denmark.

Table 5.3

Evaluation Report Format

Table of contents

- Cover sheet

- Map of location

- List of abbreviations

- Executive summary

1.		Introduction

1.1	Background for the evaluation

1.2	Brief description of the project

1.3	Evaluation methodology including general approach used, main sources of data, main instruments,

professional profile of evaluation team and limitations associated with methodology and approach

1.4	Structure of report

2.		Project relevance

2.1.	Rational and context of the project at its inception

2.2.	Changes in project context during implementation

2.3.	Relevance of project in relation to partner country priorities

2.4	Relevance of project to country programme and complementarity to support from other donors

2.5	Relevance to DANCEE priorities

3.		Efficiency

3.1.	Project progress compared to plans

3.2.	Cost and utilisation of resources compared to budget and plans

3.3.	Achievements of outputs

3.4.	Outputs in relation to resource utilisation

4.		Effectiveness

4.	1.	Expected achievements at project start

4.2	Actual or expected achievement at time of evaluation

4.3	Factors and processes affecting achievements

5.		Impact

5.1.	Priorities, needs and demands of beneficiary

5.2.	Foreseen and unforeseen impacts on the environment

5.3.	Foreseen and unforeseen impacts on the beneficiary

5.4.	Other major impacts of the project

5.5.	Factors and processes which explain project impacts

5.6.	Environmental impacts in a short term, medium term and long term perspective

6.		Sustainability

6.1.	The extend to which the project impact is/will be sustainable

6.2.	The extend to which the beneficiary can maintain project results

6.3.	Factors affecting sustainability (political, institutional, economic, technological, socio-cultural and

environmental)

7.		Lessons learned

7.1.	Operational lessons related to the project itself

7.2.	Developmental lessons related to the societal and environmental consequences of the project

7.3.	The most outstanding result or issue of the project

7.4.	The most problematic issue of the project

8.		Conclusions and recommendations

8.1.	Conclusions

8.2.	Recommendations

Annexes

- ToR for the evaluation

- Itinerary for the evaluation

- List of persons consulted

- Literature and documentation

# Footnotes

please refer to Executive Summary in Enclosure B

please refer to Statistical Summary in Section 4.3.8

FIDIC contract forms include:

- Client/Consultant Model Services Agreement (the “White FIDIC”)

- Conditions of contract for electrical and mechanical works including erection on site (the “Yellow FIDIC”)

- Conditions of contract for works of civil engineering construction (the “Red FIDIC”)

- Conditions of contract for design-build and Turn-Key (the “Orange FIDIC”).

Only for projects with a duration of more than three years or in the case of projects where problems have been identified.

The format is meant as a checklist. The evaluation team shall focus on issues of special importance to the project being evaluated.